## Sheet1
Stage | Issues | Corrections | Reference
All 3 Games | When player click urine bag on the prep trolley, animation shows that it hangs at the bedside and questions pop up | when player click urine bag from the Prep Trolley, game animated that the urine bag is placed at sterile trolley (just like all the other items) then if player click on urine bag from the sterile trolley, game animates that that the urine bag connects to the catheter and hang at the bedside, then the questions pop up | See video 'Prep trolley- urine bag'
All 3 Games | right hand and left hand icon is not working as intended | to investigate | see picture 'right hand left hand'
All 3 Games | spelling errors on hand hygiene and handrub | to correct the spelling | see picture 'typo hand hygiene', and 'typo handrub'
All 3 Games | all items dropped from the prep trolley to the sterile trolley has the foil from the packaging dangling over the trolley | to remove the foil | see sterile trolley- dropping
All 3 Games | the catheter size on the packing does not corresponds with the description | The packaging in the bin does not match the bin description. Eg: cather size 14 was found in bin indicating size 12 | see prep room- urinary catheter
All 3 Games | cannot proceed to next step after insertion of the catheter into the patient. when I tried to use the virtual joystick, the view is distorted | Important: to correct this. Also I can’t play beyond this step | see 'stage 2 after procedure'
Game 1 | after inserting the catheter into the patient, pop up question is not clear | Important: to make the wordings clearer | see 'stage 1- after insertion'
Game 2 | there is a work 'cleanpenis 0.05' | Importatnt: to remove the word 0.05 | see 'stage 2 cleaning penis'
Game 2 | the cleaning of the penis shows that it is cleaning the scrotum | Important: to animate cleaning of the ureter instead of the scrotum | see 'stage 2 cleaning penis'